## plan-timetable (1)
reference | plan | plan-event | event-date | actual-date | entry-date | notes
east-hertfordshire-district-council-local-plan-2011-plan-adopted | east-hertfordshire-district-council-local-plan-2011 | plan-adopted | 2018-10-23 | 2018-10-23 | 2026-05-14
east-hertfordshire-district-council-local-plan-2011-submit-plan-for-examination | east-hertfordshire-district-council-local-plan-2011 | submit-plan-for-examination | 2017-03-31 | 2017-03-31 | 2026-05-14
east-hertfordshire-district-council-local-plan-2011-reg-19-publication-local-plan-published | east-hertfordshire-district-council-local-plan-2011 | reg-19-publication-local-plan-published | 2016-11-03 | 2016-11-03 | 2026-05-14
east-hertfordshire-district-council-local-plan-2011-planning-inspectorate-found-sound | east-hertfordshire-district-council-local-plan-2011 | planning-inspectorate-found-sound | 2018-07-09 | 2018-07-09 | 2026-05-14
east-hertfordshire-district-council-new-local-plan-publish-notice-intention-commence | east-hertfordshire-district-council-new-local-plan | publish-notice-intention-commence | 2026-06-11 |  | 2026-05-14
east-hertfordshire-district-council-new-local-plan-scoping-consultation-start | east-hertfordshire-district-council-new-local-plan | scoping-consultation-start | 2026-06-11 |  | 2026-05-14
east-hertfordshire-district-council-new-local-plan-scoping-consultation-end | east-hertfordshire-district-council-new-local-plan | scoping-consultation-end | 2026-07-10 |  | 2026-05-14
east-hertfordshire-district-council-new-local-plan-gateway-1-self-assessment | east-hertfordshire-district-council-new-local-plan | gateway-1-self-assessment | 2026-10-15 |  | 2026-05-14
east-hertfordshire-district-council-new-local-plan-plan-content-evidence-consultation-start | east-hertfordshire-district-council-new-local-plan | plan-content-evidence-consultation-start | 2027-02-22 |  | 2026-05-14
east-hertfordshire-district-council-new-local-plan-plan-content-evidence-consultation-end | east-hertfordshire-district-council-new-local-plan | plan-content-evidence-consultation-end | 2027-04-05 |  | 2026-05-14
east-hertfordshire-district-council-new-local-plan-gateway-2-advice-sought | east-hertfordshire-district-council-new-local-plan | gateway-2-advice-sought | 2027-11-01 |  | 2026-05-14
east-hertfordshire-district-council-new-local-plan-gateway-2-advice-published | east-hertfordshire-district-council-new-local-plan | gateway-2-advice-published | 2027-12-31 |  | 2026-05-14
east-hertfordshire-district-council-new-local-plan-proposed-plan-consultation-start | east-hertfordshire-district-council-new-local-plan | proposed-plan-consultation-start | 2028-02-21 |  | 2026-05-14
east-hertfordshire-district-council-new-local-plan-proposed-plan-consultation-end | east-hertfordshire-district-council-new-local-plan | proposed-plan-consultation-end | 2028-04-17 |  | 2026-05-14
east-hertfordshire-district-council-new-local-plan-gateway-3-advice-sought | east-hertfordshire-district-council-new-local-plan | gateway-3-advice-sought | 2027-07-24 |  | 2026-05-14
east-hertfordshire-district-council-new-local-plan-gateway-3-advice-published | east-hertfordshire-district-council-new-local-plan | gateway-3-advice-published | 2028-09-29 |  | 2026-05-14
east-hertfordshire-district-council-new-local-plan-gateway-3-further-advice-sought | east-hertfordshire-district-council-new-local-plan | gateway-3-further-advice-sought |  |  | 2026-05-14 | Date unknown currently
east-hertfordshire-district-council-new-local-plan-gateway-3-repeat-advice-published | east-hertfordshire-district-council-new-local-plan | gateway-3-repeat-advice-published |  |  | 2026-05-14 | Date unknown currently
east-hertfordshire-district-council-new-local-plan-examination-submitted | east-hertfordshire-district-council-new-local-plan | examination-submitted | 2028-10-02 |  | 2026-05-14
east-hertfordshire-district-council-new-local-plan-examination-recommendations-published | east-hertfordshire-district-council-new-local-plan | examination-recommendations-published |  |  | 2026-05-14 | Date unknown currently
east-hertfordshire-district-council-new-local-plan-main-modification-consultation-start | east-hertfordshire-district-council-new-local-plan | main-modification-consultation-start |  |  | 2026-05-14 | Date unknown currently
east-hertfordshire-district-council-new-local-plan-main-modification-consultation-end | east-hertfordshire-district-council-new-local-plan | main-modification-consultation-end |  |  | 2026-05-14 | Date unknown currently
east-hertfordshire-district-council-new-local-plan-examination-pause-start | east-hertfordshire-district-council-new-local-plan | examination-pause-start |  |  | 2026-05-14 | Date unknown currently
east-hertfordshire-district-council-new-local-plan-examination-pause-end | east-hertfordshire-district-council-new-local-plan | examination-pause-end |  |  | 2026-05-14 | Date unknown currently
east-hertfordshire-district-council-new-local-plan-adopted | east-hertfordshire-district-council-new-local-plan | adopted | 2029-04-02 |  | 2026-05-14 | Estimated date
east-hertfordshire-district-council-new-local-plan-additional-consultation-start | east-hertfordshire-district-council-new-local-plan | additional-consultation-start |  |  | 2026-05-14 | Date unknown currently
east-hertfordshire-district-council-new-local-plan-additional-consultation-end | east-hertfordshire-district-council-new-local-plan | additional-consultation-end |  |  | 2026-05-14 | Date unknown currently